## TIMELINE
Thesis 12-Month Timeline
Bulan | Fase | Aktivitas | Deliverable
1-2 | Topic Selection | FINER, brainstorm, scoping | Proposal 10-15 hal
3-4 | Lit Review + Hypotheses | Synthesis matrix 30-50 papers | Bab 2 lengkap, framework
5-7 | Data Collection | Primary/secondary, cleaning | Dataset ready, codebook
8-9 | Analysis | Descriptive, main, robustness | Bab 4 draft
10 | Draft Penuh | All 5 chapters | Full thesis 100-200 hal
11 | Revision | Self-review, supervisor, polish | Final thesis
12 | Defense Prep + Sidang | Slide deck, mock, sidang | Lulus + bound

## MILESTONE_TRACKER
Milestone Tracker per Fase
Fase | Milestone | Status
Fase 1 | RQ specific dan testable | ☐
Fase 1 | Theoretical framework grounded di 5+ paper Q1 | ☐
Fase 1 | Method aligned dengan RQ | ☐
Fase 1 | Data sources confirmed accessible | ☐
Fase 1 | Proposal approved supervisor | ☐
Fase 2 | 30+ papers extracted di synthesis matrix | ☐
Fase 2 | Themes terlihat clear (3-5) | ☐
Fase 2 | Gap statement specific | ☐
Fase 2 | Hypotheses derived from theory | ☐
Fase 2 | Conceptual framework figure ready | ☐
Fase 3 | Sample size meets power | ☐
Fase 3 | Missing data <10% | ☐
Fase 3 | Codebook complete | ☐
Fase 4 | Descriptive table complete | ☐
Fase 4 | All H tested + concluded | ☐
Fase 4 | Effect size dilapor | ☐
Fase 4 | Robustness checks 3+ | ☐
Fase 5 | All 5 chapters complete | ☐
Fase 6 | Citations verified | ☐
Fase 6 | Bibliography sesuai gaya kampus | ☐
Fase 7 | Slides 15-20 ready | ☐
Fase 7 | Mock defense 2+ rounds | ☐
Fase 7 | Lulus sidang | ☐